## Dashboard
WCAG 2.2 Accessibility Audit
Interactive checklist · Levels A, AA & AAA · For Strategists, Designers, Developers & QA Teams
Project Details
Client Name | The Bank Workers Charity
Website URL | https://www.bwcharity.org.uk/
Audit Date | 2026-06-04
Auditor | Charlotte Coveney
Section | Total Items | Pass | Fail / Issue | N/A | Score
Section 1 — Content | 19 | 8 | 6 | 5 | 68% Pass
Section 2 — Design | 22 | 15 | 4 | 3 | 82% Pass
Section 3 — Development | 21 | 15 | 5 | 1 | 76% Pass
Section 4 — QA Keyboard | 10 | 5 | 5 | 0 | 50% Pass
Section 5 — QA Forms | 11 | 9 | 1 | 1 | 91% Pass
Section 6 — QA Colour | 5 | 5 | 0 | 0 | 100% Pass
Section 7 — QA Screen Reader | 11 | 7 | 3 | 1 | 73% Pass
Section 8 — QA Media | 11 | 2 | 4 | 5 | 64% Pass
TOTAL | 110 | 66 | 28 | 16 | 75% Pass
Conformance Summary
Level | Required | Pass / N/A | Fail | Not Tested | Conformance
A | 58 | 47 | 11 | 0 | Does Not Conform
AA | 37 | 27 | 10 | 0 | Does Not Conform
AAA | 4 | 0 | 4 | 0 | Does Not Conform
BP | 11 | 8 | 3 | 0 | Does Not Conform
This audit does not currently conform to WCAG 2.2 Level A.
WCAG Conformance Levels
A | Essential — assistive tech may fail without this
AA | Ideal / Legal minimum — required for most public services
AAA | Specialised — maximum inclusion target
BP | Best Practice — not formal WCAG but strongly recommended
Status Key
Pass | Criterion confirmed as meeting requirements
Fail | Criterion fails — issue found, action required
N/A | Not applicable to this project / page
Not Tested | Not yet reviewed

## Issues Log
Issues Log — WCAG Accessibility Audit
Client | The Bank Workers Charity
Website | https://www.bwcharity.org.uk/
Audit Date | 2026-06-04
Auditor | Charlotte Coveney
Fail items only — auto-populated from checklist sheets as you work through each section.
Section | WCAG Criterion | Level | Description | Owner | Status | Notes
Section 1 — Content | 1.1.1 | A | Images have meaningful alternative text (or null alt if decorative) | Content | Fail | Illustrations missing alt tags (Wellbeing Pulse pages, Get involved pages) and Wellbeing Pulse cover image. All images are decorative and therefore low priority.
Section 1 — Content | 1.2.2 | A | Captions provided for pre-recorded video with audio | Content | Fail | Client stories videos missing captions
Section 1 — Content | 1.2.5 | AA | Audio descriptions provided for pre-recorded video | Content | Fail | Client stories videos missing audio descriptions
Section 1 — Content | 2.4.4 | A | Ambiguous link text avoided; link purpose clear from link text alone | Content | Fail | "Tell me more, learn more, show me more" links on homepage should be more descriptive e.g. "Learn more about us, Read Daisy's story, Show me more client stories"
Section 1 — Content | 3.2.4 | AA | Terminology for functionality is used consistently across the service | Content | Fail | Form submission buttons vary between Submit and Sign up now/Sign up for webinar
Section 1 — Content | 3.1.5 | AAA | Content is written at an appropriate reading level (see webfx.com/tools/read-able/) | Content | Fail | Score of 40.5
Section 2 — Design | 2.4.7 | AA | Keyboard focus location is visually obvious at all times | Dev | Fail | Keyboard focus not visible on video player (client story pages), webinar filter, multiple column fields on donate form, radio buttons on sign up form/webinar forms
Section 2 — Design | 2.4.11 | AA | Focused component is not hidden or obscured by other content | Dev | Fail | Focus indicator is not visible on elements within a dropdown that is not expanded (guide pages) Focus indicator slightly obscured on homepage support dropdown
Section 2 — Design | 2.4.13 | AAA | Focus indicator has sufficient thickness and colour contrast | Dev / Designer | Fail | Focus indicator is 1px, should be minimum 2px. Blue focus indicator does not meet colour contrast against purple, but extra white outline appears on this background.
Section 2 — Design | 2.5.5 | AAA | Touch targets are at least 44×44px | Designer | Fail | Carousel buttons, social footer icons 40x40px, buttons 42px tall
Section 3 — Development | 1.4.13 | AA | Popovers on hover/focus can be dismissed via keyboard without moving focus | Developer | Fail | Popover is dimissed with tab not esc. Cannot tab through elements within the popover as tab triggers it to close
Section 3 — Development | 2.1.1 | A | All functionality is operable using the keyboard alone | Developer | Fail | Cannot tab elements within nav popover
Section 3 — Development | 2.3.3 | AAA | Animations respect the prefers-reduced-motion OS/browser setting | Developer | Fail | Animations with substantial movement should be disabled on interaction. Examples include the circular icons on the homepage and the slideup animation associated with the menu on desktop.
Section 3 — Development | 4.1.1 | A | HTML validates with no parsing errors that affect accessibility | Developer | Fail | Donation form fails validation on multiple empty heading tags and autocomplete tags being added to hidden elements. Report.
Section 3 — Development | 4.1.3 | AA | Status messages (e.g. alerts, toasts) are announced by screen readers | Developer | Fail | Error message on donate form announced as "undefined" after failed form submission
Section 4 — QA: Keyboard | 2.1.1 | A | Tab through all interactive elements — nothing is skipped | QA / Developer | Fail | Sub navigation on desktop is difficult to tab through, list items are missed.
Section 4 — QA: Keyboard | 2.1.1 | A | All buttons, links, and controls can be activated with Enter or Space | QA / Developer | Fail | Video play button does not activate
Section 4 — QA: Keyboard | 2.4.7 | AA | Focus indicator is always visible (check all states: default, hover, active) | QA / Designer | Fail | Keyboard focus not visible on video player (client story pages), webinar filter, multiple column fields on donate form, radio buttons on sign up form/webinar forms
Section 4 — QA: Keyboard | 1.4.13 | AA | Content on hover/focus (tooltips, dropdowns) can be dismissed with Esc | QA / Developer | Fail | Popover is dimissed with tab not esc. Cannot tab through elements within the popover as tab triggers it to close
Section 4 — QA: Keyboard | — | BP | Modal dialogs trap focus correctly and return focus on close | QA / Developer | Fail | Nav popover doesn't trap focus, cannot tab through elements within the popover as tab triggers it to close and tab onto next nav item
Section 5 — QA: Forms & Input | — | BP | Success confirmation is announced to screen readers via ARIA live region | QA / Developer | Fail | Third party forms do not make use or ARIA live regions
Section 6 — QA: Colour & Contrast | — | — | No issues found in this section
Section 7 — QA: Screen Reader | 1.1.1 | A | All meaningful images have descriptive alt text; decorative images have alt="" | QA / Content | Fail
Section 7 — QA: Screen Reader | 2.4.4 | A | All links and buttons have descriptive accessible names (not 'click here') | QA / Content | Fail
Section 7 — QA: Screen Reader | 4.1.3 | AA | Dynamic content updates (alerts, validation, status) are announced | QA / Developer | Fail | Error message on donate form announced as "undefined" after failed form submission
Section 8 — QA: Media | 1.2.2 | A | Pre-recorded video with audio has accurate captions | Content | Fail | Client stories videos missing captions
Section 8 — QA: Media | 1.2.3 | A | Pre-recorded video has an audio description or full text alternative | Content | Fail | Client stories videos missing audio description
Section 8 — QA: Media | 1.2.5 | AA | Pre-recorded video has a synchronised audio description track | Content | Fail | Client stories videos missing audio description
Section 8 — QA: Media | — | BP | Embedded video player is fully keyboard accessible | Developer | Fail | Cannot interact with keyboard

## Content
Section 1 — Content
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Text Alternatives & Media
1 | 1.1.1 | A | Images have meaningful alternative text (or null alt if decorative) | Content | Fail | Illustrations missing alt tags (Wellbeing Pulse pages, Get involved pages) and Wellbeing Pulse cover image. All images are decorative and therefore low priority.
2 | 1.2.1 | A | Transcripts provided for audio-only content (podcasts, recordings) | Content | N/A
3 | 1.2.1 | A | Visual-only video content has an audio or text equivalent | Content | N/A
4 | 1.2.2 | A | Captions provided for pre-recorded video with audio | Content | Fail | Client stories videos missing captions
5 | 1.2.3 | A | Audio description or text alternative available for pre-recorded video that play a functional role | Content | N/A
6 | 1.2.4 | AA | Captions provided for live video with audio (live stream content) | Content | N/A
7 | 1.2.5 | AA | Audio descriptions provided for pre-recorded video | Content | Fail | Client stories videos missing audio descriptions
Presentation & Links
8 | 1.3.3 | A | Instructions do not rely solely on shape, size, sound, location or orientation | Content | Pass
9 | 1.4.5 | AA | Images of text are not used (logos excepted) | Content | Pass
10 | 2.4.4 | A | Ambiguous link text avoided; link purpose clear from link text alone | Content | Fail | "Tell me more, learn more, show me more" links on homepage should be more descriptive e.g. "Learn more about us, Read Daisy's story, Show me more client stories"
11 | 2.4.6 | AA | Headings and labels clearly describe topic or purpose | Content | Pass
Language & Errors
12 | 3.1.1 | A | Language of page is set correctly on the html element | Dev | Pass
13 | 3.1.2 | AA | Language changes within content are marked up with correct lang codes | Content / Dev | N/A
14 | 3.2.4 | AA | Terminology for functionality is used consistently across the service | Content | Fail | Form submission buttons vary between Submit and Sign up now/Sign up for webinar
15 | 3.2.6 | A | Any help provided (e.g. FAQs, chat) is consistently positioned | Content | Pass
16 | 3.3.1 | A | Errors are identified and described to the user in text, not colour alone | Content | Pass
17 | 3.3.2 | A | Labels and instructions are visible and appropriate for all inputs | Content | Pass
18 | 3.3.3 | AA | Error messages are useful and suggest valid corrections | Content | Pass
19 | 3.1.5 | AAA | Content is written at an appropriate reading level (see webfx.com/tools/read-able/) | Content | Fail | Score of 40.5

## Design
Section 2 — Design
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Colour & Contrast
1 | 1.4.1 | A | Colour is not the sole means of conveying information | Designer | Pass
2 | 1.4.3 | AA | Text contrast meets minimum 4.5:1 (3:1 for large text) | Designer | Pass
3 | 1.4.11 | AA | Non-text UI components and focus styles meet 3:1 contrast ratio | Designer | Pass
Motion & Timing
4 | 1.4.2 | A | Audio does not play automatically | Dev | Pass | No autoplay videos
5 | 2.2.1 | A | Session timeouts can be extended or turned off | Dev | N/A | No time sensitive functionality
6 | 2.2.2 | A | Moving, blinking or auto-updating content can be paused, stopped or hidden | Dev | N/A | No carousels or moving content
7 | 2.3.1 | A | Content does not flash more than 3 times per second | Dev | Pass
Navigation & Focus
8 | 2.4.1 | A | Skip navigation mechanism provided to reach main content | Dev | Pass
9 | 2.4.3 | A | Focus order is logical, intuitive and matches visual layout | Dev | Pass
10 | 2.4.5 | AA | Multiple ways to locate a page are available (search, sitemap, nav) | Designer | Pass | Search and nav
11 | 2.4.7 | AA | Keyboard focus location is visually obvious at all times | Dev | Fail | Keyboard focus not visible on video player (client story pages), webinar filter, multiple column fields on donate form, radio buttons on sign up form/webinar forms
12 | 2.4.11 | AA | Focused component is not hidden or obscured by other content | Dev | Fail | Focus indicator is not visible on elements within a dropdown that is not expanded (guide pages) Focus indicator slightly obscured on homepage support dropdown
13 | 2.4.13 | AAA | Focus indicator has sufficient thickness and colour contrast | Dev / Designer | Fail | Focus indicator is 1px, should be minimum 2px. Blue focus indicator does not meet colour contrast against purple, but extra white outline appears on this background.
Touch & Input
14 | 2.5.1 | A | All functionality works without touch-only gestures; alternatives provided | Dev | Pass
15 | 2.5.5 | AAA | Touch targets are at least 44×44px | Designer | Fail | Carousel buttons, social footer icons 40x40px, buttons 42px tall
16 | 2.5.7 | AA | Dragging interactions have a single-pointer alternative | Designer | Pass
17 | 2.5.8 | AA | Interactive components meet minimum target size requirements (24px × 24px) | Designer / Dev | Pass
Consistency & Forms
18 | 3.2.1 | A | Focus landing on an element does not trigger a context change | Dev | Pass
19 | 3.2.3 | AA | Navigation is consistent across pages in order and labelling | Designer / Content | Pass
20 | 3.3.4 | AA | Legal or financial actions can be reversed, reviewed or confirmed | Designer | N/A | Financial actions on third party site (Stripe) not tested. No financial/legal actions on BWC site.
21 | 3.3.7 | A | Users are not required to re-enter information already provided | Designer / Dev | Pass
22 | 3.3.8 | AA | Authentication does not require a cognitive function test | Dev | Pass

## Development
Section 3 — Development
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Semantics & Structure
1 | 1.3.1 | A | Font icons are not used; SVG or image icons with alt text used instead | Developer | Pass
2 | 1.3.1 | A | Form code is semantically correct (labels, fieldsets, legends) | Developer | Pass | Forms created by pixelfridge include correct labels and legends.
3 | 1.3.1 | A | HTML structure uses correct landmarks, headings, lists, and data tables | Developer | Pass | The "How can we support you?" interactive form area and the newsletter sign-up container lack clear sectioning landmarks (like an <aside> or a <section> tag paired with an aria-labelledby). Wrapping these distinct sections in programmatic landmarks would make page scanning much smoother for screen reader users.
4 | 1.3.1 | A | Inline CSS is not used for visual-only styles that carry meaning | Developer | Pass | Where graphical elements or color are used alone to convey information, accompanying screen reader text or clear labels are provided.
5 | 1.3.2 | A | Content order in the DOM is logical and mirrors the visual sequence | Developer | Pass | JS is not used to manipulate the DOM, order reflects visual sequence
6 | 1.3.5 | AA | Autocomplete attributes applied correctly to relevant input fields | Developer | Pass | Autocomplete present on some but not all fields (varies by form). Those present are correct
Text & Zoom
7 | 1.4.4 | AA | Text can be resized to 200% without loss of content or functionality | Developer | Pass
8 | 1.4.10 | AA | Content reflows at 400% zoom without horizontal scrolling or loss | Developer | Pass
9 | 1.4.13 | AA | Popovers on hover/focus can be dismissed via keyboard without moving focus | Developer | Fail | Popover is dimissed with tab not esc. Cannot tab through elements within the popover as tab triggers it to close
Keyboard & Interaction
10 | 2.1.1 | A | All functionality is operable using the keyboard alone | Developer | Fail | Cannot tab elements within nav popover
11 | 2.1.2 | A | Keyboard focus is never trapped (except intentional modal dialogs) | Developer | Pass
12 | 2.3.3 | AAA | Animations respect the prefers-reduced-motion OS/browser setting | Developer | Fail | Animations with substantial movement should be disabled on interaction. Examples include the circular icons on the homepage and the slideup animation associated with the menu on desktop.
13 | 2.5.2 | A | Actions are triggered on pointer up (not down) unless cancellable | Developer | Pass
14 | 2.5.3 | A | Visible labels are included in the accessible name of controls | Developer | Pass
15 | 3.2.1 | A | No context changes triggered by element receiving focus | Developer | Pass
ARIA & Validation
16 | 4.1.1 | A | HTML validates with no parsing errors that affect accessibility | Developer | Fail | Donation form fails validation on multiple empty heading tags and autocomplete tags being added to hidden elements. Report.
17 | 4.1.2 | A | All UI components have correct name, role and value exposed to AT | Developer | Pass | All buttons have clear, descriptive labels. For buttons without visible text labels, title attributes and aria-label attributes have been provided to ensure accessibility.
18 | 4.1.2 | A | Custom controls use WAI-ARIA correctly and are fully keyboard operable | Developer | N/A
19 | 4.1.3 | AA | Status messages (e.g. alerts, toasts) are announced by screen readers | Developer | Fail | Error message on donate form announced as "undefined" after failed form submission
Best Practice
20 | — | BP | Windows High Contrast Mode does not break the interface | Developer | Pass | Testing in high contrast and website is full usable without any issues.
21 | — | BP | HTML lang attribute set on root element and language changes inline | Developer | Pass

## QA_Keyboard
Section 4 — QA: Keyboard
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Keyboard Navigation
1 | 2.1.1 | A | Tab through all interactive elements — nothing is skipped | QA / Developer | Fail | Sub navigation on desktop is difficult to tab through, list items are missed.
2 | 2.1.1 | A | All buttons, links, and controls can be activated with Enter or Space | QA / Developer | Fail | Video play button does not activate
3 | 2.1.2 | A | Focus never becomes trapped outside of intentional modal dialogs | QA / Developer | Pass
4 | 2.4.3 | A | Focus order follows the logical visual reading sequence | QA / Developer | Pass
5 | 2.4.7 | AA | Focus indicator is always visible (check all states: default, hover, active) | QA / Designer | Fail | Keyboard focus not visible on video player (client story pages), webinar filter, multiple column fields on donate form, radio buttons on sign up form/webinar forms
6 | 2.4.11 | AA | Focused element is not obscured by sticky headers, banners or overlays | QA / Developer | Pass
7 | 1.4.13 | AA | Content on hover/focus (tooltips, dropdowns) can be dismissed with Esc | QA / Developer | Fail | Popover is dimissed with tab not esc. Cannot tab through elements within the popover as tab triggers it to close
Best Practice
8 | — | BP | Skip to main content link appears on first Tab keypress | QA / Developer | Pass
9 | — | BP | Modal dialogs trap focus correctly and return focus on close | QA / Developer | Fail | Nav popover doesn't trap focus, cannot tab through elements within the popover as tab triggers it to close and tab onto next nav item
10 | — | BP | Custom components (carousels, accordions) follow ARIA design patterns | QA / Developer | Pass | Accordions have clear aria-labels including open & close labels

## QA_Forms
Section 5 — QA: Forms & Input
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Form Labels & Errors
1 | 3.3.2 | A | All form fields have a visible, persistent label (not placeholder-only) | QA / Content | Pass
2 | 3.3.1 | A | Errors are clearly identified and described in text next to / above the field | QA / Content | Pass
3 | 3.3.3 | AA | Error suggestions tell users exactly how to correct invalid input | QA / Content | Pass
4 | 3.3.4 | AA | Confirmation step provided before submitting financial or legal actions | QA / Designer | N/A | Third party site (stripe) used for financial actions, not tested
5 | 3.3.7 | A | User is not asked to re-enter data already provided in the same session | QA / Designer | Pass
6 | 3.3.8 | AA | Login / authentication does not require solving a cognitive test (e.g. CAPTCHA) | QA / Designer | Pass
7 | 1.3.5 | AA | Autocomplete attributes on name, email, address and phone fields are correct | QA / Developer | Pass | Autocomplete present on some but not all fields (varies by form). Those present are correct
8 | 4.1.2 | A | Required fields are marked programmatically (aria-required or required attr) | QA / Developer | Pass
9 | 1.3.1 | A | Related fields are grouped with fieldset and legend elements | QA / Developer | Pass
Best Practice
10 | — | BP | Error summary provided at top of page on submission failure | QA / Content | Pass | Summary on Donate form and browser error message on Get help form. Hubspot forms (webinars) do not show summary.
11 | — | BP | Success confirmation is announced to screen readers via ARIA live region | QA / Developer | Fail | Third party forms do not make use or ARIA live regions

## QA_Colour
Section 6 — QA: Colour & Contrast
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Contrast Ratios
1 | 1.4.3 | AA | Normal text (below 18pt / 14pt bold): contrast ratio ≥ 4.5:1 | Designer / QA | Pass
2 | 1.4.3 | AA | Large text (18pt+ / 14pt+ bold): contrast ratio ≥ 3:1 | Designer / QA | Pass
3 | 1.4.11 | AA | UI components (buttons, inputs, icons) have ≥ 3:1 contrast against background | Designer / QA | Pass
4 | 1.4.11 | AA | Focus indicators have ≥ 3:1 contrast against adjacent colours | Designer / QA | Pass | Blue focus indicator does not meet colour contrast against purple, but extra white outline appears on this background.
5 | 1.4.1 | A | Information is not conveyed by colour alone (e.g. red = error) | Designer / QA | Pass

## QA_ScreenReader
Section 7 — QA: Screen Reader
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Screen Reader Checks
1 | 1.1.1 | A | All meaningful images have descriptive alt text; decorative images have alt="" | QA / Content | Fail
2 | 1.3.1 | A | Page structure (landmarks, headings, lists) is announced correctly | QA / Developer | Pass
3 | 2.4.2 | A | Page title is unique, descriptive and announced on page load | QA / Content | Pass
4 | 2.4.4 | A | All links and buttons have descriptive accessible names (not 'click here') | QA / Content | Fail
5 | 3.1.1 | A | Screen reader announces content in the correct human language | QA / Developer | Pass
6 | 3.1.2 | AA | Inline language changes are announced correctly by the screen reader | QA / Developer | N/A
7 | 4.1.2 | A | Custom controls expose correct role, name and state to screen readers | QA / Developer | Pass
8 | 4.1.3 | AA | Dynamic content updates (alerts, validation, status) are announced | QA / Developer | Fail | Error message on donate form announced as "undefined" after failed form submission
9 | 2.5.3 | A | Visible button/link labels match or are included in the accessible name | QA / Developer | Pass
Best Practice
10 | — | BP | Test with VoiceOver + Safari (iOS/macOS) | QA | Pass | Tested, see note below
11 | — | BP | Reading order announced by screen reader matches visual reading order | QA / Developer | Pass | Screen reader can announce everything that's accesible to it - it currently get's stuck within the menu. Tabbing is an acceptable route down the page.

## QA_Media
Section 8 — QA: Media
# | WCAG Criterion | Level | Description / What to Check | Owner | Status | Notes
Audio & Video
1 | 1.2.1 | A | Podcast / audio-only content has a full transcript available | Content | N/A
2 | 1.2.1 | A | Silent video has a text description of all visual content | Content | N/A
3 | 1.2.2 | A | Pre-recorded video with audio has accurate captions | Content | Fail | Client stories videos missing captions
4 | 1.2.3 | A | Pre-recorded video has an audio description or full text alternative | Content | Fail | Client stories videos missing audio description
5 | 1.2.4 | AA | Live video with audio has captions (real-time) | Content | N/A
6 | 1.2.5 | AA | Pre-recorded video has a synchronised audio description track | Content | Fail | Client stories videos missing audio description
Animation & Autoplay
7 | 1.4.2 | A | No audio or video plays automatically on page load | Designer | Pass
8 | 2.2.2 | A | Autoplay content (animations, carousels) can be paused or stopped | Designer | N/A
9 | 2.3.1 | A | No content flashes more than 3 times per second | Designer / Developer | Pass
Best Practice
10 | — | BP | Captions are styled for readability (contrast, size, positioning) | Content | N/A
11 | — | BP | Embedded video player is fully keyboard accessible | Developer | Fail | Cannot interact with keyboard

## Testing Tools
Testing Tools & Resources
The resources below provide a range of tools to help test against multiple success criteria within the WCAG 2.2 accessibility guidelines. While these tools can assist in identifying issues and validating compliance, it’s important to note that many criteria require manual testing to ensure a fully accessible and inclusive experience.
Tool | Test / Use | Description
Image alt checker | Alt text available on images | Tool for testing that alt text is present on all images, the test is run on a per page basis
Readability Test | Content is written at an appropriate reading level | Web service that grades content on a scale of 0 - 100. Ideally a pass rate should be 60+
Colour contrast checker | Background and foreground colour contast checker | Web service that allows for background and foregound colours to be graded against A,AA & AAA requirements. Text sizing and weight can also be compared.
HTML validator | Valadate HTML structure | W3C validator, must be run a per page basis
Voiceover | Apple default screen reader | Default screen reader which can be used to test voice over compatability
Arc browser testing suite | Full page test | Great for testing structure and best practices in the browser directly. This tool will also flag any minor issues such as missing labels or alt text.
Wave page tester | Full page test | Tool which will highlight contrast, labels and alt text. Very useful for checking heading structure.